## Project Timeline
SDEV2004 – Group Project Plan ¦ Group of 4
Phase 1 Due: Wed 18 Mar 2026 @ 11:00 ¦ Phase 2 Due: Wed 29 Apr 2026 @ 11:00 ¦ Worth: 35% of module
Week | Dates | Phase | Group Tasks | Member 1 | Member 2 | Member 3 | Member 4 | Key Deliverable | Internal Deadline | Status | Notes
3 | 09–13 Feb | Setup | Form group, agree communication channel, set up GitHub repo | Repo setup | README skeleton | Meeting notes doc | Confirm members | GitHub repo live | 13 Feb | ✅ Done | Agree on branch strategy
4 | 16–20 Feb | Phase 1 | Select target area, choose 2 cultural dimensions, 2 countries & languages | Research area options | Draft PoV statements | Hofstede research | Hall research | Target area agreed | 20 Feb | 🔄 In Progress | Document all decisions
5 | 23–27 Feb | Phase 1 | Define design & dev guidelines (folder structure, Flask template inheritance, i18n strategy) | Flask folder structure | base.html template | babel.cfg / gettext setup | CSS/style guide | Dev guidelines draft | 27 Feb | ⬜ Not Started | Avoid hardcoded pages
6 | 02–06 Mar | Phase 1 | Individual analysis: each member analyses an existing website in target area | Analyse Site A (Hofstede) | Analyse Site B (Hall) | Analyse Site C (UX heuristics) | Analyse Site D (combined) | 4 individual analyses | 06 Mar | ⬜ Not Started | Apply recognised models
7 | 09–13 Mar | Phase 1 | Finalise group PDF (PoV, hypotheses, guidelines). Compile individual PDFs | Merge group doc → PDF | Individual PDF (M2) | Individual PDF (M3) | Individual PDF (M4) + M1 | All PDFs ready | 11 Mar | ⬜ Not Started | Internal deadline 1 wk early!
8 | 16–18 Mar | Phase 1 | ⭐ SUBMIT Phase 1 by Wed 18 Mar @ 11:00. Attend lab discussion with TA | Upload group PDF | Upload individual PDF | Upload individual PDF | Upload individual PDF | 🚨 Phase 1 Submission | 18 Mar 11:00 | ⬜ Not Started | Must attend lab discussion
9 | 23–27 Mar | Phase 2 | Begin Flask app: integrate base template, language switcher, translations skeleton | app.py / __init__.py | base.html + nav | Language switcher logic | translations/ .pot file | App skeleton running | 27 Mar | ⬜ Not Started | Test language switch early
10 | 30 Mar–03 Apr | Phase 2 | Individual pages: each member builds their culturally adaptive page | Page 1 (Member 1) | Page 2 (Member 2) | Page 3 (Member 3) | Page 4 (Member 4) | 4 pages in progress | 03 Apr | ⬜ Not Started | Commit to branches, not main
11 | 06–10 Apr | Phase 2 | Integration sprint: merge all pages, test language switching end-to-end | Integration merge | Fix translation gaps | Cross-browser test | Cultural adapt review | Integrated app running | 10 Apr | ⬜ Not Started | Test on 2+ machines
12 | 13–17 Apr | Phase 2 | Cultural adaptation polish: layout, colour, imagery, symbols per culture | Layout tweaks | Colour/imagery checks | Symbol/text review | UX consistency audit | Adaptations complete | 17 Apr | ⬜ Not Started | Must be intentional, not cosmetic
13 | 22–24 Apr | Phase 2 | README finalisation, code comments, peer evaluation prep | README sections 1-5 | README sections 6-9 | Individual contribution comments | requirements.txt + final test | README complete | 24 Apr | ⬜ Not Started | README is primary marking reference
14 | 28–29 Apr | Phase 2 | ⭐ DEMO Tue 28 Apr (lecture). SUBMIT + peer evaluate Wed 29 Apr @ 11:00 | Demonstrate app | Evaluate another group | Submit ZIP | Attend all sessions | 🚨 Phase 2 Submission | 29 Apr 11:00 | ⬜ Not Started | All 4 must attend demo

## Responsibilities
SDEV2004 – Group Responsibilities & Task Assignment
Area | Task | Member 1 | Member 2 | Member 3 | Member 4
Communication | Set up group chat (WhatsApp/Discord) | Lead | Support | Support | Support
Communication | Record meeting decisions | Rotate | Rotate | Rotate | Rotate
Communication | Flag missed deadlines / issues | All | All | All | All
Phase 1 – Group | Select target area & rationale | All | All | All | All
Phase 1 – Group | Define cultural dimensions + 2 countries | Lead | Support | Support | Support
Phase 1 – Group | Write PoV statements & hypotheses | Support | Lead | Support | Support
Phase 1 – Group | Write design & dev guidelines | Support | Support | Lead | Support
Phase 1 – Group | Compile & submit group PDF | Support | Support | Support | Lead
Phase 1 – Individual | Analyse existing website (cultural/UX) | M1 site | M2 site | M3 site | M4 site
Phase 1 – Individual | Submit individual PDF | M1 | M2 | M3 | M4
Phase 2 – App | Set up Flask app skeleton (app.py) | Lead | — | — | Support
Phase 2 – App | base.html template + navigation | — | Lead | — | Support
Phase 2 – App | Language switcher & gettext config | — | — | Lead | Support
Phase 2 – App | Static assets (CSS, images, style guide) | Support | Support | — | Lead
Phase 2 – Pages | Individual culturally adaptive page 1 | Lead | — | — | —
Phase 2 – Pages | Individual culturally adaptive page 2 | — | Lead | — | —
Phase 2 – Pages | Individual culturally adaptive page 3 | — | — | Lead | —
Phase 2 – Pages | Individual culturally adaptive page 4 | — | — | — | Lead
Phase 2 – Integration | Merge all pages into single app | Lead | Support | Support | Support
Phase 2 – Integration | Test language switching (all pages) | All | All | All | All
Phase 2 – Integration | Test on multiple machines | All | All | All | All
Phase 2 – Docs | README sections 1–5 | Lead | Support | — | —
Phase 2 – Docs | README sections 6–9 + individual contributions | — | — | Lead | Support
Phase 2 – Docs | requirements.txt & final checks | — | Lead | — | Support
Phase 2 – Submission | Upload ZIP to Brightspace | Lead | — | — | —
Phase 2 – Evaluation | Peer evaluate another group's app | All | All | All | All
Phase 2 – Demo | Demonstrate integrated application | All | All | All | All

## Penalty Tracker
SDEV2004 – Penalty Awareness Tracker
Phase | Risk Item | Applies To | Penalty | Mitigation Action | Responsible | Status
Phase 1 | Failure to submit group documentation | Group | −ALL Phase 1 marks | Submit by 11 Mar (internal). Check Brightspace upload success. | All members | ⬜ Pending
Phase 1 | Failure to submit individual documentation | Individual | −5% of Phase 1 mark | Each member submits own PDF by 11 Mar (internal). | Each member | ⬜ Pending
Phase 1 | Miss lab discussion with TA on 18 Mar | Individual | −5% of Phase 1 mark | Attend lab Wed 18 Mar. Note TA schedule published in advance. | Each member | ⬜ Pending
Phase 1 | Entire group fails to attend lab discussion | Group | −10% of Phase 1 mark | Ensure all 4 members attend 18 Mar lab. | All members | ⬜ Pending
Phase 2 | Failure to submit group application + docs | Group | −ALL Phase 2 marks | Submit ZIP by 27 Apr (internal). Test upload on lab machine. | All members | ⬜ Pending
Phase 2 | Failure to demonstrate integrated app | Group | −20% of Phase 2 mark | Integrate early (Week 11). Demo in lab 28–29 Apr. | All members | ⬜ Pending
Phase 2 | Individual fails to attend/participate in demo | Individual | −10% of Phase 2 mark | All 4 members attend Tue 28 Apr / Wed 29 Apr. | Each member | ⬜ Pending
Phase 2 | Fail to complete peer evaluation | Individual | −5% of Phase 2 mark | Complete Brightspace survey during lab 28 Apr. | Each member | ⬜ Pending
Phase 2 | Entire group fails peer evaluation | Group | −10% of Phase 2 mark | Ensure all 4 evaluate another group's app. | All members | ⬜ Pending
Phase 2 | App does not run on lecturer's machine | Group | Up to −10% of Phase 2 | Test on lab machines. Include requirements.txt. Clear setup docs. | All members | ⬜ Pending

## Submission Checklists
SDEV2004 – Submission Checklists
PHASE 1 – GROUP SUBMISSION (due 18 Mar)
# | Checklist Item | Responsible | Done ✓
1 | Single PDF named e.g. Group1-Phase1.pdf | All | ⬜
2 | Uploaded via Brightspace | Nominated member | ⬜
3 | Group number + student names & numbers included | All | ⬜
4 | Selected target area and rationale documented | All | ⬜
5 | Cultural contexts defined (2 dimensions, 2 countries, 2 languages) | All | ⬜
6 | PoV statements included | All | ⬜
7 | Testable hypotheses included | All | ⬜
8 | Design & dev guidelines: code structure | All | ⬜
9 | Design & dev guidelines: i18n/l10n strategy | All | ⬜
10 | Design & dev guidelines: cultural adaptation | All | ⬜
11 | Design & dev guidelines: UX consistency | All | ⬜
12 | Individual contribution definitions included | All | ⬜
13 | Evidence of group decision-making included | All | ⬜
14 | Optional wireframes/sketches included (if used) | All | ⬜
PHASE 1 – INDIVIDUAL SUBMISSION (due 18 Mar)
# | Checklist Item | Responsible | Done ✓
1 | Single PDF named e.g. D1234567-Phase1.pdf | Each member | ⬜
2 | Uploaded via Brightspace | Each member | ⬜
3 | Analysis of existing website in target area | Each member | ⬜
4 | Cultural model(s) applied (Hofstede, Hall, etc.) | Each member | ⬜
5 | Strengths identified | Each member | ⬜
6 | Weaknesses identified | Each member | ⬜
7 | Usability implications identified | Each member | ⬜
8 | Explains how analysis informed group decisions | Each member | ⬜
9 | Student's individual contribution clearly documented | Each member | ⬜
PHASE 2 – GROUP APPLICATION SUBMISSION (due 29 Apr)
# | Checklist Item | Responsible | Done ✓
1 | Single ZIP named e.g. Group1-Phase2.zip | All | ⬜
2 | Uploaded via Brightspace | Nominated member | ⬜
3 | Flask app with organised folder structure | All | ⬜
4 | app/ with main Python entry point | All | ⬜
5 | templates/ with HTML using template inheritance | All | ⬜
6 | static/ with only assets actually used | All | ⬜
7 | translations/ with compiled .mo and .po files | All | ⬜
8 | babel.cfg and any config files included | All | ⬜
9 | requirements.txt reflecting actual dependencies | All | ⬜
10 | README.md included (see README checklist) | All | ⬜
11 | No .venv, __pycache__, or unused assets | All | ⬜
12 | App tested on lab machine / second machine | All | ⬜
13 | Dynamic language switching works | All | ⬜
14 | Cultural adaptation changes by language/country | All | ⬜
PHASE 2 – README CHECKLIST
# | Checklist Item | Responsible | Done ✓
1 | 1. Project Overview (target area, description) | All | ⬜
2 | 2. Cultural Scope (languages, countries, models) | All | ⬜
3 | 3. Design Rationale (PoV, hypotheses, cultural reasoning) | All | ⬜
4 | 4. Architecture & Structure | All | ⬜
5 | 5. Internationalisation & Localisation Strategy | All | ⬜
6 | 6. Cultural Adaptation Mechanisms | All | ⬜
7 | 7. Individual Contributions (subsection per student) | All | ⬜
8 | 8. Setup & Execution Instructions | All | ⬜
9 | 9. Limitations & Future Work | All | ⬜
PHASE 2 – INDIVIDUAL CODE DOCUMENTATION
# | Checklist Item | Responsible | Done ✓
1 | File-level comment identifying author | Each member | ⬜
2 | Inline comments on culturally adaptive logic | Each member | ⬜
3 | Comments explain key design decisions | Each member | ⬜
4 | Comments explain cultural assumptions | Each member | ⬜
5 | Comments show where/how hypotheses are addressed | Each member | ⬜
6 | README Individual Contributions subsection accurate | Each member | ⬜